## Product_Backlog
PRODUCT BACKLOG
User Epic	ID	Title User Story	User Story	Prority	Estimate Story Point	Acceptance Criteria	Status	Sprint n°
Basic operation / of the program	1	Interface of GUI	As a user, I want this application has a GUI, / so that I can automate a simple task	1-Highest	3	Given the user opens the application, / When the user interacts with the application's interface, / Then the system should display a Graphical User Interface (GUI) for easy interaction.	Done	1
Basic operation / of the program	2	Create Rules	As a user, I want the ability to create a set of rules, each consisting of / a trigger and an associated action, so that I can define automated / tasks tailored to my specific needs within the application	1-Highest	3	Given the user is in the application's rule creation interface, / When the user inputs a trigger and associates a specific action to / create a rule, / Then the application should save the rule with the / defined trigger and action	Done	1
Basic operation / of the program	3	Check Triggers	As a user, I want the application to periodically check the rules I've / defined, so that it can automatically execute the corresponding / action if the trigger conditions are met	1-Highest	3	Given the user has defined rules within the application, / When the application periodically checks the defined rules for trigger conditions, / Then the application should automatically execute the corresponding action for any rule where the trigger conditions are met	Done	1
Basic operation / of the program	4	Define Trigger by / time	As a user, I want to define a trigger for a rule by specifying a particular / time of the day so that the rule can be fired when the current time / matches the specified time	1-Highest	2	Given the user is configuring a rule in the application, / When the user specifies a particular time of the day as the trigger for the rule, / Then the application should recognize the specified time, and the rule should be designed to be fired when the current time matches the specified time	Done	1
Basic operation / of the program	5	Set Action (Play / Audiofile)	As a user, I want to set up an action for a rule that involves playing a / specified audio file when the rule is fired.	1-Highest	3	Given the user is configuring a rule within the application, / When the user sets up an action for the rule, / Then the user should be able to specify playing a specified audio file as the action, / and the application should be designed to execute this action when / the rule is fired	Done	1
Basic operation / of the program	6	Set Action (Show Dialog)	As a user, I want to set up an action for a rule that involves displaying a specified / message in a dialog box when the rule is fired	1-Highest	1	Given the user is configuring a rule within the application, / When the user sets up an action for the rule, / Then the user should be able to / specify displaying a specified message in a dialog box as the action	Done	1
Edit and permanent storage of the rules	7	Edit the Set of Rules	As a user, I want the capability to edit existing rules so that I can / manage and customize rule settings according to my preferences	2-Critical	3	Given the user is in the application, / When the user wishes to add new rules, / Then the application should provide the capability to add new rules.	Done	1
					Given the user is in the application, / When the user wants to delete existing rules, / Then the application should provide the capability to entirely remove rules.
Edit and permanent storage of the rules	8	Set a Status Rule	As a user, I want to be able to set a rule as active or inactive / so that I can determine when the rule should be operational / based on my preferences.	2-Critical	2	Given the user is managing rules within the application, / When the user desires to control the operational status of a rule, / Then the application should provide the ability to set a rule as / either active or inactive.	Done	1
Edit and permanent storage of the rules	9	Save Rules	As a user, I want the ability to save my rules so that I can easily / retrieve them when I reopen the app.	2-Critical	8	Given the user is managing rules within the application, / When the user wants to save the rules / Then the application should persistently store the rules in a manner / that survives the closure and reopening of the application / and upon reopening the app, the rules should be automatically / loaded and visible in the rule management section	Done	1
Edit and permanent storage of the rules	10	Set Rules Fired / only once	As a user, I want to be able to specify whether a rule should only be / triggered once or whether it can be triggered again after a sleep period, / so that I have control over the reusability and run times of the rules / based on my preferences	2-Critical	8	Given the user is configuring a rule within the application, / When the user sets up the rule, / Then the user should be able to specify whether the rule must be fired / only once, preventing its execution again even if the trigger becomes / true, or if it can be fired again after a designated 'sleeping' period / specified in days, hours, and minutes.	Done	1
More actions and more triggers	11	Set Action Specified / String	As a user, I want to set up an action for a rule that writes a specified string at / the end of a specified text file, so that I can add information / about an existing file	3-High	3	Given the user is configuring a rule within the application, / When the user sets up an action for the rule by specifying writing a / specified string at the end of a designated text file, / Then the application should successfully execute the rule, / and the specified string should be accurately appended to the / specified text file	Done	2
More actions and more triggers	12	Set Action Copy File	As a user, I want to to set up an action for a rule to copy a / specified file from a defined source directory to a specified destination / directory so that I can efficiently manage my tasks	3-High	2	Given the user is configuring a rule within the application, / When the user sets up an action for the rule to copy a specified file / from a defined source directory to a specified destination directory, / Then the application should successfully execute the action when / the rule is triggered, and the specified file should be accurately / copied from the defined source directory to the specified destination directory.	Done	2
More actions and more triggers	13	Set Action Move File	As a user, I want to setup an action for a rule to move a specified file from a defined source directory so that I can organize the environment / according to my preferences.	3-High	2	Given the user is configuring a rule within the application, / When the user sets up an action for the rule to move a specified file from a defined source directory, / Then the application should successfully execute the action when the rule is triggered, / And the specified file should be accurately moved from the defined source directory to a destination	Done	2
More actions and more triggers	14	Set Action Delete File	As a user, I want setup an action for a rule to delete a specified file from a specified directory / so that I can automate the removal of unnecessary when a rule is triggered	3-High	2	Given the user is configuring a rule within the application, / When the user sets up an action for the rule to delete a specified file from a defined directory, / Then the application should successfully execute the action when the rule is triggered, / And the specified file should be accurately deleted from the specified directory	Done	2
More actions and more triggers	15	Set Action Run / External / Program	As a user, I want setup an action for a rule to run a specified external / program, with specified command line arguments, so that I can / automate the execution of / external programs when a rule is triggered	3-High	13	Given that the user wants to set an action by defining an external program with predefined command line arguments, when the activation condition is satisfied, then the application should automatically execute the specified external program and evaluate its exit status	Done	2
More actions and more triggers	16	Set Trigger Day	As a user, I want to set triggers based on the current day of the / week being a specific day, so that I can automate actions to occur / on specific days of the week.	3-High	2	Given that the user wants to automate actions based on the current / day of the week, / When the user sets triggers that activate based on specific days / of the week, / Then the system should be able to / automatically trigger actions on those specific days.	Done	2
More actions and more triggers	17	Set Trigger Month	As a user, I want the capability to set triggers based on the current day of / the month being a specified day, so that I can automate actions to happen / on specific days within a month.	3-High	2	Given the user wants to automate actions based on the day of / the month, / When the user sets triggers that activate based on specific / days of the month, then the system should be able to automatically / execute actions on those specific days of the month.	Done	2
More actions and more triggers	18	Set Trigger Date	As a user, I want to establish triggers based on the current date being / a specified date , so that I can automate actions for particular date	3-High	2	Given the user wants to automate actions based on the specific date, / When the user sets triggers that activate based on the specific day of the date, / Then the system should automatically execute actions on specific days of the entire date.	Done	2
More actions and more triggers	19	Trigger Existence File	As a user, I want to trigger an action based on the existence of a file with / a specified name in a designated directory, allowing me to automate / processes when certain files are present.	3-High	3	Given the user wants to configure the trigger with the designated / directory and specified file, / When a file with the same name is detected / in the same designated directory, / Then the trigger should activate the / associated action linked to the detected file.	Done	2
More actions and more triggers	20	Trigger Size File	As a user, I want to activate an action if the size of a particular file exceeds / a specified value so that I can manage large files automatically.	3-High	3	Given the user wants to define a trigger specifying the file name and / a size threshold, When the file size exceeds the indicated threshold / value, / When the system should automatically trigger the designated / action.	Done	2
More actions and more triggers	21	Trigger on External / Program	As a user, I want to trigger an action based on the successful execution / of a specified external program with predefined command-line / arguments, so that actions can be activated based on the exit / status of the program.	3-High	5	Given the user wants to define a trigger specifying an external program / to execute with predefined command-line arguments, / When the trigger becomes true, / Then the application should successfully execute the / external program, evaluate the exit status of the program, and return / a specific value (0=Failed, 1=Success).	Done	2
Combined actions and triggers	22	Action Sequence	As a user, I want to create a sequence of actions that includes multiple / elementary actions and sub-sequences, allowing me to design complex / workflows for automation.	4-Medium	13	Given that the user is using the application and has access to the / feature of creating a sequence of actions, When they include a series / of elementary actions and sub-sequences, / Then the sequence of actions / is automatically saved in the system and executed successfully.	Done	3
Combined actions and triggers	23	Logical Operation / Trigger	As a user, I want to apply logical operations between elementary / triggers or combination of elementary triggers, so that I can establish / conditional rules, enabling precise activation of actions.	4-Medium	13	Given the user intends to activate rules based on trigger values, / When they apply the logical NOT operation to a single trigger or / combined triggers, / Then the system should activate subsequent actions only if the / negated trigger condition is not met.	Done	3
					Given the user intends to activate rules based on trigger values, / When they combine multiple triggers using the logical OR operation, / Then the system should activate subsequent actions if at least one / of the trigger conditions is satisfied.
					Given the user intends to activate rules based on trigger values, / When they combine multiple triggers using the logical AND operation, / Then the system should activate subsequent actions only if all trigger / conditions are satisfied.
Counters	24	Create Counters	As a user, I want to define counters as named variables with integer values, / so that I can manage and keep track of various values within the system.	5-Low	2	Given the user wishes to define counters as integer-type variables, / When they input the counter's name and an integer value, / Then the system should be able to keep track of this counter to / monitor various values within the system.	Done	3
Counters	25	View Counters	As a user, I desire the ability to view the current value of a / counter, so that I can monitor values accurately as needed.	5-Low	2	Given the user wishes to view the current value of a counter, / When they ask the system to display a specific counter, / Then the system should be able to show the integer value of the / counter to accurately monitor values as required.	Deleted	3
Counters	26	Modify Counters	As a user, I desire the ability to view and modify the current value of a / counter, so that I can update values accurately as needed.	5-Low	2	Given the user wants to modify the current value of a counter, / When they ask the system to change the current value of a specific / counter, / Then the system should be able to update the current value of that / counter to accurately track values as required.	Done	3
Counters	27	Set Counter	As a user, I want the capability to set a particular counter to a defined value, / so that I can precisely manage and control the counter's value as / needed for my tasks.	5-Low	2	Given that the user wants to set a specific counter to a defined value, / When they ask the system to set that counter, / Then the system must be able to correctly set the counter, / enabling precise management and control of the counter's value.	Done	3
Counters	28	Increment Counter	As a user, I want to add a specific number to the value of a designated counter / so that I can increment its value according to my requirements.	5-Low	2	Given the user desire to add a specific number to the value of a designated counter, / When they request the system to perform such an increment, / Then the system must be able to add the specified number / to the current value of the counter.	Done	3
Counters	29	Combine Counter / Values	As a user, I want to perform actions such as adding the value of a specified / counter to another specified counter,so that I can perform more complex / operations by combining different counter values.	5-Low	3	Given the user wants to perform actions such as adding the value of a / specified counter to another specified counter, / When they ask the system to add the value of one counter to another, / Then the system must be able to perform the operation and / update the value of the second counter.	Done	3
Counters	30	Comparison	As a user, I want to set triggers based on comparisons between values, / so that I can automate actions based on these predefined conditions	5-Low	2	Given the user who wants to set triggers based on value comparisons, / When they define a trigger that activates upon a specific condition, / Then the system must be able to automatically execute the / associated action.	Done	3
Counters	31	Counter Comparison	As a user, I want to set triggers based on comparisons between counters, / so that I can automate actions based on these predefined conditions	5-Low	3	Given the user who wants to set triggers based on counters comparisons, / When they define a trigger that activates upon a specific condition, / Then the system must be able to automatically execute the / associated action.	Done	3
Counters	32	String Value / Insertion	As a user, I want to utilize variable substitution in actions involving strings to / dynamically insert the current counter value, so that I can have updated / counter values within strings, providing increased flexibility in actions.	5-Low	8	Given the user wants to use variable substitution within string-based / actions, / When the user dynamically inserts a "special" character, / Then the system should promptly update these strings with the current / counter value, thereby enhancing the adaptability of actions related / to counters.	Done
					127

## 1st_Sprint
				Legend:
Sprint Backlog					Review
Sprint n°1					Similar
Sprint Goal	User Story ID	User Story	Type Task	Task	Status	Estimete Effort / Total Estimated: 36 / Total Done:36	Assigned		Completed
Basic Operation / and Edit Rules	1	As a user, I want this application has a GUI, / so that I can automate a simple task	User Story Task	Implementing the starting FXML file of the / application with SceneBuilder	Completed	3	Alessandro Passannante
	2	As a user, I want the ability to create a set of rules, each consisting of / a trigger and an associated action, so that I can define automated / tasks tailored to my specific needs within the application	User Story Task	Implement the Rule class	Completed	3	Alessandro Passannante
				Implement the RuleSet class
				Develop the creation of an istance of the object Rule from the GUI
				Implement the Trigger and Action interface/ abstract class
	3	As a user, I want the application to periodically check the rules I've / defined, so that it can automatically execute the corresponding / action if the trigger conditions are met	User Story Task	Create a thread in the setrules class to periodically check trigger conditions	Completed	3	Alessia Lettieri
	4	As a user, I want to define a trigger for a rule by specifying a particular / time of the day so that the rule can be fired when the current time / matches the specified time	User Story Task	Implement the CurrentDayTime and its method (returns a boolean value)	Completed	2	Alessandro Passannante
	5	As a user, I want to set up an action for a rule that involves playing a / specified audio file when the rule is fired.	User Story Task	Implement ActionPlayAudio class and its methods	Completed	3	Alessia Lettieri
	6	As a user, I want to set up an action for a rule that involves displaying a specified / message in a dialog box when the rule is fired	User Story Task	Implement ActionShowDialog class	Completed	1	Alessandro Passannante
	7	As a user, I want the capability to edit existing rules so that I can / manage and customize rule settings according to my preferences	User Story Task	Implement addRule()	Completed	3	Alessia Lettieri
				Implement deleteRule()
				Implement update the GUI
	8	As a user, I want to be able to set a rule as active or inactive / so that I can determine when the rule should be operational / based on my preferences.	User Story Task	Implement active field (boolean)	Completed	2	Domenico Napolitano
				Implement the active() and deactive() method	Completed		Marco Panico
	9	As a user, I want the ability to save my rules so that I can easily / retrieve them when I reopen the app.	User Story Task	Implement the SaveRule class	Completed	8	Domenico Napolitano
				Implement the saveRules() method
				Implement the loadRules() method
	10	As a user, I want to be able to specify whether a rule should only be / triggered once or whether it can be triggered again after a sleep period, / so that I have control over the reusability and run times of the rules / based on my preferences	User Story Task	Implement fired_only_once boolean field, fired_oo_status / boolean field on Rule class	Completed	8	Marco Panico
				Implement sleeping boolean field and / sleeping_Date LocalDateTime field on Rule class
				Update ""checkrules()"" method on RuleSet class

## 2nd_Sprint
Sprint Backlog
Sprint n°2
Sprint Goal	User Story ID	Title User Story	User Story	Type Task	Task	Status	Estimete Effort / Total Estimated:39 / Total Done:	Assigned
More actions and more triggers	11	Set Action Specified / String	As a user, I want to set up an action for a rule that writes a specified string at / the end of a specified text file, so that I can add information / about an existing file	User Story Task	Create SpecifiedStringAction class	Completed	3	Alessandro Passannante		Legend:
					Add GUI interaction					Review
	12	Set Action Copy File	As a user, I want to set up an action for a rule to copy a / specified file from a defined source directory to a specified destination / directory so that I can efficiently manage my tasks	User Story Task	Create CopyFileAction class	Completed	2	Marco Panico		Similar
					Add GUI elements in View and Controller					Completed
	13	Set Action Move File	As a user, I want to setup an action for a rule to move a specified file from a defined source directory so that I can organize the environment / according to my preferences.	User Story Task	Create MoveFileAction class	Completed	2	Marco Panico
					Add GUI elements in View and Controller
	14	Set Action Delete File	As a user, I want setup an action for a rule to delete a specified file from a / specified directory / so that I can automate the removal of unnecessary when a rule is triggered	User Story Task	Create DeleteFileAction class	Completed	2	Marco Panico
					Add GUI elements in View and Controller
	15	Set Action Run / External / Program	As a user, I want setup an action for a rule to run a specified external / program, with specified command line arguments, so that I can / automate the execution of / external programs when a rule is triggered	User Story Task	Create RunExternalProgramAction class	Completed	13	Domenico Napolitano
					Add GUI elements of View and Controller			Marco Panico
	16	Set Trigger Day	As a user, I want to set triggers based on the current day of the / week being a specific day, so that I can automate actions to occur / on specific days of the week.	User Story Task	Create TriggerDay class	Completed	2	Alessia Lettieri
					Add GUI elements to View and Controller
	17	Set Trigger Month	As a user, I want the capability to set triggers based on the current day of / the month being a specified day, so that I can automate actions to happen / on specific days within a month.	User Story Task	Create TriggerMonth class	Completed	2	Alessia Lettieri
					Add GUI elements to View and Controller
	18	Set Trigger Date	As a user, I want to establish triggers based on the current date being / a specified date , so that I can automate actions for particular date.	User Story Task	Create TriggerDate class	Completed	2	Alessia Lettieri
					Add GUI elements to View and Controller
	19	Trigger Existence File	As a user, I want to trigger an action based on the existence of a file with / a specified name in a designated directory, allowing me to automate / processes when certain files are present.	User Story Task	Create TriggerExistence class	Completed	3	Alessandro Passannante
					Add GUI elements to View and Controller
	20	Trigger Size File	As a user, I want to activate an action if the size of a particular file exceeds / a specified value so that I can manage large files automatically.	User Story Task	Create TriggerSizeFile class	Completed	3	Alessandro Passannante
					Add GUI elements to View and Controller
	21	Trigger on External / Program	As a user, I want to trigger an action based on the successful execution / of a specified external program with predefined command-line / arguments, so that actions can be activated based on the exit / status of the program.	User Story Task	Create TriggerExternalProgram class	Completed	5	Domenico Napolitano
					Add GUI elements to View and Controller			Alessia Lettieri

## 3th_Sprint
Sprint Backlog
Sprint n°3
Sprint Goal	User Story ID	Title User Story	User Story	Type Task	Task	Status	Estimete Effort / Total Estimated: 44 / Total Done:	Assigned
Combinations and / counters	22	Action Sequence	As a user, I want to create a sequence of actions that includes multiple / elementary actions and sub-sequences, allowing me to design complex / workflows for automation.	User Story Task	Create a Class that permits multiple actions	Completed	13	Alessia Lettieri
				User Story Task	Implements GUI elements that permit the user to insert multiple actions
	23	Logical Operation / Trigger	As a user, I want to apply logical operations between elementary / triggers or combination of elementary triggers, so that I can establish / conditional rules, enabling precise activation of actions.	User Story Task	Create the NotTrigger Class	Completed	13	Alessanndro Passannante
				User Story Task	ClassCreate a CompositeTrigger Class
				User Story Task	Add the GUI elements that permits the user to combine multiple triggers
	24	Create Counters	As a user, I want to define counters as named variables with integer values, / so that I can manage and keep track of various values within the system.	User Story Task	Create a Counter Class	Completed	2	Domenico Napolitano
				User Story Task	Add GUI elements that permit the creation of a counter
	25	View Counters	As a user, I desire the ability to view the current value of a / counter, so that I can monitor values accurately as needed.	User Story Task	Add GUI elements that permit the view of the created counters	Deleted	2
	26	Modify Counters	As a user, I desire the ability to modify the current value of a / counter, so that I can update values accurately as needed.	User Story Task	Create ModifyClass	Completed	2	Domenico Napolitano
					Modify the GUI so that the user can directly edit the value of a counter
	27	Set Counter	As a user, I want the capability to set a particular counter to a defined value, / so that I can precisely manage and control the counter's value as / needed for my tasks.	User Story Task	Create SetCounterValueAction class	Completed	2	Domenico Napolitano
				User Story Task	Add GUI elements in View and Controller
	28	Increment Counter	As a user, I want to add a specific number to the value of a designated counter / so that I can increment its value according to my requirements.	User Story Task	Create AddValueCounterAction class	Completed	2	Domenico Napolitano
				User Story Task	Add GUI elements in View and Controller
	29	Combine Counter / Values	As a user, I want to perform actions such as adding the value of a specified / counter to another specified counter,so that I can perform more complex / operations by combining different counter values.	User Story Task	Create SumCountersAction class	Completed	3	Marco Panico
				User Story Task	Add GUI elements in View and Controller
	30	Comparison	As a user, I want to set triggers based on comparisons between values, / so that I can automate actions based on these predefined conditions	User Story Task	Create TriggerCounterCompValues class	Completed	2	Marco Panico
				User Story Task	Add GUI elements in View and Controller
	31	Counter Comparison	As a user, I want to set triggers based on comparisons between counters, / so that I can automate actions based on these predefined conditions	User Story Task	Create TriggerCountersCompare class	Completed	3	Marco Panico
				User Story Task	Add GUI elements in View and Controller

Extra	32	String Value Insertion	As a user, I want to utilize variable substitution in actions involving strings to dynamically insert the current counter value, so that I can have updated counter values within strings, providing increased flexibility in actions.	User Story Task	Create a ReplaceAction class for every String based action	Completed	8	Alessanndro Passannante
				User Story Task	Add the GUI elements for every single implemented class			Alessia Lettieri

## Chart
	Total story Point missing	ESTIMATE STORY POINT	EFFECTIVE STORY POINT
SPRINT	TOTAL STORY POINT MISSING	ESTIMATE STORY POINT	EFFECTIVE STORY POINT
1 SPRINT	127	36	36
2 SPRINT	96	39	39
3 SPRINT	52	44	50

EXTENDED BURNDOWN CHART

BurnDown Chart I Sprint

BurnDown Chart II Sprint

BurnDown Chart III Sprint